## Goals
SPRINT | GOALS | Due Date
1 | Brand Identity | 5/11/2021
Wireframes
Front End - Homepage
| Database Design | 10/11/2021
Login Features
Dashboard - Admin Panel
Lisitng Page
2 | Database Update | 14/11/2021
| Product Details - Page | 16/11/2021
| Admin Panel | 17/11/2021
| Lisitng Page - Design Update | 16/11/2021
About Page
Contact Page
Admin Panel Wireframe
Front End - Design Update
3 | Cars of the world
Cars of the world
Cars of the world
Cars of the world
Cars of the world
Cars of the world
4 | Cars of the world
Cars of the world
Cars of the world
Cars of the world
Cars of the world
Cars of the world
Cars of the world

## Sprint BurnDown
Sprint 1 (Time In Hours)
Tasks | Assigned to | Time (Hours) | Status | Comments
GOAL - Brand Identity
Logo Design | Abjith | 1 | Completed
Finding Fonts | Abjith | 0.5 | Completed
GOAL - Wireframe Design
Wireframe - Homepage | Sajaad Khan | 2 | Completed
Wireframe - Lisitng Page | Jeni Patel | 2 | Completed
Wireframe - Details Page | Jeni Patel | 2 | Completed
Wireframe - Contact Page | Gaganpreet Kaur | 0.5 | Completed
Wireframe - About Page | Gaganpreet Kaur | 0.5 | Completed
Wireframe - Admin Login | Gaganpreet Kaur | 0.5 | Completed
Wireframe - Admin Dashboard | Abjith | 3 | In Progress
Wireframe - Checkout Page | Abjith | 1 | Due | To be done once the listing page is ready
Front End - Homepage | Sajaad Khan | 72 | Completed
Front End - Lisitng Page | Jeni Patel | 48 | Completed
Front End - Admin Panel | Gaganpreet Kaur | 72 | In Progress
Front End - Contact Page | Gaganpreet Kaur | 24 | In Progress
Front End - About Us Page | Abjith | 24 | In Progress
Database Desgin - Stage 1 | Sajaad Khan & Jeni Patel | 72 | Completed
UI Testing | Abjith | 24 | In Progress
Sprint 2 (Time In Hours)
Tasks | Assigned to | Time (Hours) | Status
GOAL - Ui/UX Stage 2
Database Design Update for listing page | Sajaad Khan, Jeni Patel | 24 | In Progress
Database Design Update for product details | Jeni Patel | 15 | In Progress
Front End Page Design Update Stage 2 | Sajaad Khan | 5 | Completed
Login Pages | Gaganpreet Kaur | 3 | Completed
Admin Panel Wireframes | Abjith, Gaganpreet Kaur | 3 | Completed
UI Testing for homepage | Abjith | 1 | Completed
UI Testing for Lisitng Page | Abjith, Jeni Patel | 4 | In Progress
Front End Admin Panel Dashboard | Gaganpreet Kaur | 4 | In Progress
Data Collecting and Data Upload | Abjith, Sajaad Khan | 8 | Due
About Page Wireframe and Front End Design | Gaganpreet Kaur, Abjith, Sajaad, Jeni | 6 | In Progress
Contact Page Wireframe and Front End Design | Gaganpreet Kaur, Abjith, Sajaad | 4 | In Progress
Sprint 3 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL - Ui/UX Stage 3
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
Lorem Ipsum | xyz | 1 | Completed
Lorem Ipsum | pqr | 0.5 | Due
Lorem Ipsum | abc, pqr, xyz | 0.5 | Completed
Lorem Ipsum | pqr, xyz | 1 | Completed
Lorem Ipsum | abc, pqr, xyz | 1 | Completed
Lorem Ipsum | pqr, xyz | 2 | In Progress
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
GOAL - Lorem Ipsum
Lorem Ipsum | xyz | 0.5 | In Progress
Lorem Ipsum | pqr | 1 | In Progress
Lorem Ipsum | abc, pqr, xyz | 2 | In Progress
Lorem Ipsum | pqr, xyz | 0.5 | In Progress
Sprint 4 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL - Ui/UX Stage 4
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
Lorem Ipsum | xyz | 1 | Completed
Lorem Ipsum | pqr | 0.5 | Due
Lorem Ipsum | abc, pqr, xyz | 0.5 | Completed
Lorem Ipsum | pqr, xyz | 1 | Completed
Lorem Ipsum | abc, pqr, xyz | 1 | Completed
Lorem Ipsum | pqr, xyz | 2 | In Progress
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
GOAL - Lorem Ipsum
Lorem Ipsum | xyz | 0.5 | In Progress
Lorem Ipsum | pqr | 1 | In Progress
Lorem Ipsum | abc, pqr, xyz | 2 | In Progress
Lorem Ipsum | pqr, xyz | 0.5 | In Progress

## Product Backlog
ID | Description | Sprint | Status
1 | Deleting function for deleting products from Admin Panel | 1 | In Progress
2 | Database Update - Modifying Tables for Data Entry | 2 | In Progress

## Challenges
Challenges Faced | Time Invested | Status | Solution
Site Responsivenss | 2 days | Solved | Adding Bootstrap
Database connectivity | 1 day | Solved | Normalization
Data Deletion function | 2 days | Solved | Using Ajax with proper java script
Adding images from admin panel | 2 hours | In Progress | More research
Car Listing Page Layout | 1 day | In Progress | More research & Wireframe design
Formatting the landing page on clicking the links without opening a new page | 3 hours | Solved | Added php functions
Database Update - Modifying Tables for Data Entry | 4 hours | In Progress | Organizing Data for entries